## Slide 1: Project 2
Cadden Buist

## Slide 2: What are expected goals and objectives of the project?
Develop a new Financial app from the current one
3 New features
Customize 5 current features
Design with logo

## Slide 3: Meet the Team
Software Architect – Michael Lee
Technical Team Lead – To Be Decided(TBD)
Software Developers – TBD
Software Testers – TBD
UI Design and Development Team – TBD
Project Manager (ABC Workflow v3.0) – Julia Smith
Team Lead (ABC Workflow v3.0) – Ryan Hernandez

## Slide 4: Initial Schedule
Expected Start Date – March 1st
Expected End Date December 15th
Task | Estimated efforts (work weeks)
Requirements Analysis | 1 – March 8
UI design and development | 3- March 29th
Feature 1 Development | 10 -June 7
Feature 2 Development | 8 - August 2
Feature 3 Development | 7 - September 20
Feature Customization 1 | 6 – August 9
Feature Customization 2 | 6 – September 20
Feature Customization 3 | 4 – November 1
Feature Customization 4 | 3 – November 29
Feature Customization 5 | 1 – December 6
Software System Testing | 1- December 15th

## Slide 5
Chart: Gantt chart
| Requirement Analysis | UI Design and Development | Feature 1 Development | Feature 2 Development | Feature 3 Development | Feature Customization 1 | Feature Customization 2 | Feature Customization 3 | Feature Customization 4 | Feature Customization 5 | Software System Test
Start Date | 45352 | 45359 | 45387 | 45460 | 45530 | 45471 | 45513 | 45562 | 45597 | 45618 | 45625
Duration (days) | 7 | 28 | 73 | 70 | 49 | 42 | 42 | 35 | 21 | 7 | 16

## Slide 6
Risk | Status of Risk | Affected Project (Yes or No) | Affected Schedule
Software Compatibility | Unchanged | No | No
Resource Availability | Unchanged | No | No
Software isn’t ready in time for launch | Project delay | Yes | Yes
Progress is slowed down because of the ABC workflow v3.0 members unable to find time for XYZ | Unchanged | No | No
Team Members Quit | Unchanged | No | No
Project Sponsors give up on the project | Unchanged | No | No

## Slide 7: Team Spirit
There are no current issues involving the team or my leadership. Everyone is getting along well, and we have been able to get through minor inconveniences with the project.

## Slide 8: New Issues arising?
There have been some setbacks that we were not expecting to derail us from this project.
Feature 2 development is more complex than originally thought
Customization 3 will now take 5 workweeks
System testing will need at least a week and a half
UI design and development will need another week due to client approval
3 days of extra work is needed for Feature 1
We will be working on some projects at the same time to make up for the extra time

## Slide 9
Task | Estimated efforts (work weeks)
Requirements Analysis | 1 – March 8
UI design and development | 4- April 5
Feature 1 Development | 10.5 -June 17
Feature 2 Development | 10 - August 26
Feature 3 Development | 7 – October 14
Feature Customization 1 | 6 – August 9
Feature Customization 2 | 6 – September 20
Feature Customization 3 | 5 – November 1
Feature Customization 4 | 3 – November 22
Feature Customization 5 | 1 – November 29
Software System Testing | 2 - December 15th

## Slide 10: Actions Taken
We will be starting the customize features a few weeks after beginning feature 2 development
We plan to leave at least 2 weeks for software testing
We plan on working some extra hours, if need be, to catch up with our work
We will use any extra time not planned out for catchup or to get ahead of the project.